## Phase012
Structure Fracture Control Evaluation Form for Small Satellite deployed from J-SSOD
| Satellite Name : DRAGONFLY【Phase 0/1/2】 | JAXA Structure and Fracture Control Board (JAXA SFCB) | Form Ver. June 17, 2024
|  | Signature | DATE
| JAXA SFCB Chair | 和田 勝 /WADA Masaru | 2024-06-18
| Satellite Project Manager |  | 2024-06-17
If all of condition A) to G) are fulfilled or approved waiver, this form can be applicable instead of Fracture Control Summary Report.
If any of condition H) to M) are applicable, correspondent verifications must be implemented.
Check | Title | Condition | Verification Document | Remarks
| A) Soft Stowed Launch | Launched with stowed in softbag. | [Phase 012] Closed, Document No. :09_BIRDSX-SAR-01 Section4 Safety Assessment Report for Phase012 (2024/6/17) [Phase 3] Open, Document No. :16_BIRDSX-SAR-02 Safety Assessment Report for Phase3 (To be closed at Ph3) | ソフトバッグ打ち上げであること Checked for all CubeSats because they are packed in softbag.
| B) Mass | Less than 1.33kg per 1U. | [Phase 3] Open, J-SSOD&BIRDS-X Interface Verification Record Document No. : 19_BIRDSX-IVR-01(To be closed at Ph3) | 1U体積あたり1.33kg以下であること
| C) Neither Pressure System nor Pressure Vessel | With neither Pressure System nor Pressure Vessel | [Phase 012] Closed, Document No. :09_BIRDSX-SAR-01 Section5 Safety Assessment Report for Phase012 (2024/6/17) [Phase 3] Open, Document No. :16_BIRDSX-SAR-02 Safety Assessment Report for Phase3 (To be closed at Ph3) | 圧力システム、圧力容器いずれも有さない
| D) No Hazardous Materials | No toxic or biological material except for electrolyte of battery. | [Phase 012] Closed, Document No. :09_BIRDSX-SAR-01 Section5 Safety Assessment Report for Phase012 (2024/6/17) [Phase 3] Open, Document No. :16_BIRDSX-SAR-02 Safety Assessment Report for Phase3 (To be closed at Ph3) | バッテリー電解液以外にハザードとなるMaterials(Toxic, Biological)を有さない
| E) Minimum Stress History | H/W is not exposed to the stress environment other than the followings: 1) Random vibration test 2) Ground Transportation 3) Launch(1 time) | [Phase 012] Closed, Document No. :09_BIRDSX-SAR-01 Section5 Safety Assessment Report for Phase012 (2024/6/17) [Phase 3] Open, Document No. :16_BIRDSX-SAR-02 Safety Assessment Report for Phase3 (To be closed at Ph3) | ライフサイクルにおいて、以下を越える環境に晒されない ①ランダム振動試験 ②地上輸送 ③１回の打ち上げ
- | F) Low Risk Fracture Part | Outer structure meets the following criteria:(as Low Risk Fracture Part) | ー | 最外構造はLow Risk Fracture Partとして以下の条件を満たす
| F-1) Maximum Stress | Total tensile stresses are no greater than 30% of ultimate tensile strength | [Phase012] Closed, Document No. :02_BIRDSX-SR-01 Section5.5.2 Structural Analysis Report (2024/5/28) | ライフサイクルの最大引張応力終局強度の30%以下である
| F-2) Material | Aluminum alloy and A-rated in MSFC-HDBK-527/JSC09604/CR-99117 or Table-I in MSFC-STD-3029 | [Phase012]Closed, Document No. :03_BIRDSX-MIUL-01 MIUL (2024/1/10) | レーティングAのアルミ構造である
| F-3) Material Processing | Not using a process such as welding, forging, casting, or quenching heat treatment | [Phase012] Closed, Document No. :02_BIRDSX-SAR-01 Section3.2.1 Safety Assessment Report for Phase012 (2024/6/17) | 溶接、鍛造、鋳造、焼入れは行っていない
| F-4) Visual Inspection | No defects or surface damage is detected by visual inspection | [Phase3] Open, Document No. :25_BIRDSX-VT-01 Vibration Test Report (To be closed at Ph3) | 外観目視で欠陥がないことを確認している なお、キット品利用の場合；キット品のみではなく、衛星システムに対して実施
| G) No Delta Pressure Hazard | No hazard is identified regarding the delta-pressure during launch, pressurization/ depressurization in airlock. | [Phase 012] Closed, Document No. :09_BIRDSX-SR-01 Section5.3 Structural Analysis Report(2024/5/28) | ライフサイクル（打ち上げ、モジュールの加減圧等）によって発生する差圧によるハザードはない
If the satellite consists of the following items, applicable section ( H) to N) ) should be fulfilled.
applicable | H) Shatterable Structure | Shatterable Structure (Camera Lens, Solar Cell Cover etc.) | ー | Shatterable Structureをもつか？（レンズ、太陽電池セルカバー等）
| H-1) Vibration Test | 1. Verified by visual inspection after vibration test under the condition specified in JX-ESPC-101132/101133 | [Phase3] Open, Document No. :25_BIRDSX-VT-01 Vibration Test Report (To be closed at Ph3) | 以下のいずれかの制御 ①JPAHに規程された環境条件で振動試験をパスする ②Low Risk Fracture Partにより封入されている
applicable | J) Deployment Structure | Deployment restraint wire whose fracture could cause hazard. |  | 誤展開がハザードにつながる展開機構（テグス）を持つか？もし誤展開ハザードが識別されていない場合はチェックしない。 If deployment does not cause hazard, do not need to check a box.
| J-1) Fail Safe Approach | Redundant wire | [Phase 012] Closed, Document No. :06_BIRDSX-AP-01Section4.3, 4.4 Assembly Procedure(2024/6/7) [Phase 3] Open, Document No. :18_BIRDSX-AR-01 Assembly Record (To be closed at Ph3) | 展開機構の拘束機構として２本のテグスを使用している
| J-2) Proof Test | Each wire is proof-tested and visual-inspected | [Phase 3] Open, Document No. :27_BIRDSX-WTR-01 Wire Strength Test Report (To be closed at Ph3) | １本のテグスに対してFCPに従った試験を行い、パスしている
| J-3) Assembly Procedure | Wire handling process is defined in assembly procedure. | [Phase 012] Closed, Document No. :06_BIRDSX-AP-01 Section 4.3, 4.4 Assembly Procedure(2024/6/7) [Phase 3] Open, Document No. :18_BIRDSX-AR-01 Assembly Record (To be closed at Ph3) | 組み立て手順書にテグスの取り扱いを明記している
| J-4) Round | (If any) The part touching the wire is rounded appropriately. | [Phase 012] Closed, Document No. :06_BIRDSX-AD-01(Page14-17) Assembly Procedure(2024/01/29) [Phase 3] Open, Document No. :18_BIRDSX-AR-01 Assembly Record (To be closed at Ph3) | テグスに接触する箇所がある場合、適切に面取りしている（該当する場合のみ）
| J-5) Loosening Prevention | (If any) Loose prevention is provided on the tied portion. | [Phase 012] Closed, Document No. :06_BIRDSX-AP-01 Section 4.4 Assembly Procedure(2024/6/7) [Phase 3] Open, Document No. :18_BIRDSX-AR-01 Assembly Record (To be closed at Ph3) | テグスに結び目がある場合、ゆるみ止めを施している（該当する場合のみ）
applicable | K) Fail Safe Fastener | Fail Safe Fastener | ー | Fail Safe Fastenerがあるか？
| K-1) Fail Safe Analysis | K-1) Fail safety analysis shows MS >0. (F.S = 1.0) | [Phase012] Closed, Document No. :02_BIRDSX-SR-01 Section 5.5.3 Structural Analysis Report (2024/5/28) | 以下のいずれかの制御 ①(K-1)Fail Safe Analysisをパスする ②(K-2)MWLとMEFLを考慮した振動試験をパスする なお、キット品利用の場合；キット品のみではなく、衛星システムに対して実施
| K-2) Quality Control | Quality Control meets the condition L-2) to L-5). | Please refer from L-2) to L-5). | 適切な品質管理をしている（L-2～L-5に適合）
applicable | L) Safety Critical Fastener | Safety Critical Fastener | ー | Safety Critical Fastenerがあるか？
| L-1-1) Secondary Locking Feature | L-1-1b) Locking compound of which the application process MUA is approved. | ②Loctite263 [Phase 012] Closed, Document No. :06_BIRDSX-AP-01 Assembly Procedure(2024/6/7) [Phase 3] Open, Document No. :18_BIRDSX-AR-01 Assembly Record (To be closed at Ph3) | 制御は2次ゆるみ止めか振動試験のいずれかを選択できる。2次ゆるみ止め選択した場合、以下のいずれかの検証を行うこと ①(L-1-1a)ロックヘリサートなどの摩擦型ゆるみ止め機構の場合はランニングトルクの計測を行う ②(L-1-1b)非摩擦型のロッキングコンパウンドは、使用環境に適合したものを使用し、取扱説明書等で指定されている塗布工程通りに取り扱う または、MWLとMEFLを考慮した振動試験をパスしている（L-1-2）。 なお、キット品利用の場合；キット品のみではなく、衛星システムに対して実施
| L-2-1) Certificates for fastener materials | L-2-1) Certificates for fastener materials | [Phase 3] Open, Document No. :18_BIRDSX-AR-01 Assembly Record (To be closed at Ph3) | ファスナの材料証明 または、MWLとMEFLを考慮した振動試験をパスしている。 なお、キット品利用の場合；キット品のみではなく、衛星システムに対して実施
| L-3) Torque mark inspection | L-3) Torque mark inspection | [Phase 012] Closed, Document No. :06_BIRDSX-AP-01 Assembly Procedure(2024/6/7) [Phase 3] Open, Document No. :18_BIRDSX-AR-01 Assembly Record (To be closed at Ph3) [Phase3] Open, Document No. :25_BIRDSX-VT-01 Vibration Test Report (To be closed at Ph3) | 振動試験後の外観検査によってトルクマークにより緩みがないことを確認している（試験レベルはMEFLでよい）
| L-4) Fastening torque control | L-4) Fastening torque control | [Phase 012] Closed, Document No. :06_BIRDSX-AP-01 Section4.1.7 Assembly Procedure(2024/6/7) [Phase 3] Open, Document No. :18_BIRDSX-AR-01 Assembly Record (To be closed at Ph3) | トルク管理している
| L-5) Fastener traceability | L-5) Fastener traceability | [Phase 012] Closed, Document No. :06_BIRDSX-AP-01 Section4.1.3 Assembly Procedure(2024/6/7) [Phase 3] Open, Document No. :18_BIRDSX-AR-01 Assembly Record (To be closed at Ph3) | 材料証明のあるファスナを設計どおり使用している
applicable | M) Sealed Container | Sealed Container |  | Sealed Containerがあるか？
| M-1) Container characteristic | Single, Independent Container containing a non-hazardous substance. |  | Single, Independent Container containing a non-hazardous substance.
| M-2) Stored Energy | Contain less than 19,310 Joules(14,240 foot-pounds) of stored energy |  | Contain less than 19,310 Joules(14,240 foot-pounds) of stored energy
| M-3) Maximum delta pressure | Maximum delta pressure is less than 1.5atm(22psia, 1.5bars) |  | less than 1.5atm(22psia, 1.5bars)
applicable | N) Fracture Critical Part | Fracture Critical Part |  | Fracture Critical Partがあるか？（Solar cellカバーガラスおよびカメラレンズはH)に該当）
| N-1) Design Verification | Verified by Structural Analysis with appropriate mechanical properties | [Phase012] Closed, Document No. :02_BIRDSX-SR-01 Section 5.4 Structural Analysis Report (2024/5/28) | 構造解析（強度・剛性）に用いる機械的特性データが妥当であるか確認する。
| N-2) Production Verification | Verified by appropriate material selection and production process | [Phase 3] Open, Document No. :18_BIRDSX-AR-01 Assembly Record (To be closed at Ph3) | 適切な製造装置および材料で、製作されていることを確認する
| N-3) Product Verification | Verified by visual inspection after vibration test under the condition specified in JX-ESPC-101132/101133 Visual Inspection and NDE(Tapping test acceptable) before and after Tests | [Phase3] Open, Document No. :25_BIRDSX-VT-01 Vibration Test Report (To be closed at Ph3) | フライト品(特に搭載部品との複雑な結合部等)が健全に製作されていることを確認する なお、キット品利用の場合；キット品のみではなく、衛星システムに対して実施

## Phase3
Structure Fracture Control Evaluation Form for Small Satellite deployed from J-SSOD
| Satellite Name : DRAGONFLY【Phase 3】 | JAXA Structure and Fracture Control Board (JAXA SFCB) | Form Ver. September 20, 2024
|  | Signature | DATE
| JAXA SFCB Chair | 和田 勝 / WADA Masaru | September 22, 2024
| Satellite Project Manager |  | 2024-09-20
If all of condition A) to G) are fulfilled or approved waiver, this form can be applicable instead of Fracture Control Summary Report.
If any of condition H) to M) are applicable, correspondent verifications must be implemented.
Check | Title | Condition | Verification Document | In Japanese
| A) Soft Stowed Launch | Launched with stowed in softbag. | [Phase 3] Closed, Document No. : 16_DRAGONFLY-SAR-02 Flight Safety Assessment Report for Phase 3 (2024/07/30) | ソフトバッグ打ち上げであること
| B) Mass | Less than 1.33kg per 1U. | [Phase 3] Closed, Document No. : 19_DRAGONFLY-IVR-01 J-SSOD & 001J DRAGONFLY Interface Verification Record (2024/03/30) | 1U体積あたり1.33kg以下であること
| C) Neither Pressure System nor Pressure Vessel | With neither Pressure System nor Pressure Vessel | [Phase 3] Closed, Document No. : 16_DRAGONFLY-SAR-02 Flight Safety Assessment Report for Phase 3 (2024/07/30) | 圧力システム、圧力容器いずれも有さない
| D) No Hazardous Materials | No toxic or biological material except for electrolyte of battery. | [Phase 3] Closed, Document No. : 16_DRAGONFLY-SAR-02 Flight Safety Assessment Report for Phase 3 (2024/07/30) | バッテリー電解液以外にハザードとなるMaterials(Toxic, Biological)を有さない
| E) Minimum Stress History | H/W is not exposed to the stress environment other than the followings: 1) Random vibration test 2) Ground Transportation 3) Launch(1 time) | [Phase 3] Closed, Document No. : 16_DRAGONFLY-SAR-02 Flight Safety Assessment Report for Phase 3 (2024/07/30) | ライフサイクルにおいて、以下を越える環境に晒されない ①ランダム振動試験 ②地上輸送 ③１回の打ち上げ
- | F) Low Risk Fracture Part | Outer structure meets the following criteria:(as Low Risk Fracture Part) | ー | 最外構造はLow Risk Fracture Partとして以下の条件を満たす
| F-1) Maximum Stress | Total tensile stresses are no greater than 30% of ultimate tensile strength | [Phase012] Closed, Document No. :02_BIRDSX(DRAGONFLY)-SR-01 Section5.5.2 Structural Analysis Report (2024/5/28) | ライフサイクルの最大引張応力終局強度の30%以下である
| F-2) Material | Aluminum alloy and A-rated in MSFC-HDBK-527/JSC09604/CR-99117 or Table-I in MSFC-STD-3029 | [Phase012]Closed, Document No. :03_BIRDSX(DRAGONFLY)-MIUL-01 (2024/1/10) | レーティングAのアルミ構造である
| F-3) Material Processing | Not using a process such as welding, forging, casting, or quenching heat treatment | [Phase012] Closed, Document No. :02_DRAGONFLY-SAR-01 Section3.2.1 Safety Assessment Report for Phase012 (2024/6/17) | 溶接、鍛造、鋳造、焼入れは行っていない
| F-4) Visual Inspection | No defects or surface damage is detected by visual inspection | [Phase 3] Closed, Document No. : 25_DRAGONFLY-VT-01 Vibration Test Report (2024/03/21) | 外観目視で欠陥がないことを確認している なお、キット品利用の場合；キット品のみではなく、衛星システムに対して実施
| G) No Delta Pressure Hazard | No hazard is identified regarding the delta-pressure during launch, pressurization/ depressurization in airlock. | [Phase 012] Closed, Document No. :09_BIRDSX(DRAGONFLY)-SR-01 Section5.3 Structural Analysis Report(2024/5/28) | ライフサイクル（打ち上げ、モジュールの加減圧等）によって発生する差圧によるハザードはない
If the satellite consists of the following items, applicable section ( H) to N) ) should be fulfilled.
applicable | H) Shatterable Structure | Shatterable Structure (Camera Lens, Solar Cell Cover etc.) | ー | Shatterable Structureをもつか？（レンズ、太陽電池セルカバー等）
| H-1) Vibration Test | 1. Verified by visual inspection after vibration test under the condition specified in JX-ESPC-101132/101133 | [Phase3] Closed, Document No. :25_DRAGONFLY-VT-01 Vibration Test Report (2024/03/21) | 以下のいずれかの制御 ①JPAHに規程された環境条件で振動試験をパスしている ②Low Risk Fracture Partにより封入されている
applicable | J) Deployment Structure | Deployment restraint wire whose fracture could cause hazard. |  | 誤展開がハザードにつながる展開機構（テグス）を持つか？
| J-1) Fail Safe Approach | Redundant wire | [Phase 012] Closed, Document No. :06_BIRDSX(DRAGONFLY)-AP-01Section4.3, 4.4 Assembly Procedure(2024/6/7) [Phase 3] Closed, Document No. :18_DRAGONFLY-AR-01 Assembly Record (2024/03/16) | 展開機構の拘束機構として２本のテグスを使用している
| J-2) Proof Test | Each wire is proof-tested and visual-inspected | [Phase 3] Closed, Document No. :27_DRAGONFLY-WTR-01 Wire Strength Test Report (2024/03/27) | １本のテグスに対してFCPに従った試験を行い、パスしている
| J-3) Assembly Procedure | Wire handling process is defined in assembly procedure. | [Phase 012] Closed, Document No. :06_BIRDSX(DRAGONFLY)-AP-01 Section 4.3, 4.4 Assembly Procedure(2024/6/7) [Phase 3] Closed, Document No. :18_DRAGONFLY-AR-01 Assembly Record (2024/03/16) | 組み立て手順書にテグスの取り扱いを明記している
| J-4) Round | (If any) The part touching the wire is rounded appropriately. | [Phase 012] Closed, Document No. :06_BIRDSX(DRAGONFLY)-AD-01(Page14-17) Assembly Procedure(2024/01/29) [Phase 3] Closed, Document No. :18_DRAGONFLY-AR-01 Assembly Record (2024/03/16) | テグスに接触する箇所がある場合、適切に面取りしている（該当する場合のみ）
| J-5) Loosening Prevention | (If any) Loose prevention is provided on the tied portion. | [Phase 012] Closed, Document No. :06_BIRDSX(DRAGONFLY)-AP-01 Section 4.4 Assembly Procedure(2024/6/7) [Phase 3] Closed, Document No. :18_DRAGONFLY-AR-01 Assembly Record (2024/03/16) | テグスに結び目がある場合、ゆるみ止めを施している（該当する場合のみ）
applicable | K) Fail Safe Fastener | Fail Safe Fastener | ー | Fail Safe Fastenerがあるか？
| K-1) Fail Safe Analysis | K-1) Fail safety analysis shows MS >0. (F.S = 1.0) | [Phase012] Closed, Document No. :02_BIRDSX(DRAGONFLY)-SR-01 Section 5.5.3 Structural Analysis Report (2024/5/28) | Fail Safe Analysisをパスしている、または、MWLとMEFLを考慮した振動試験をパスしている。 なお、キット品利用の場合；キット品のみではなく、衛星システムに対して実施
| K-2) Quality Control | Quality Control meets the condition L-2) to L-5). | Please refer from L-2) to L-5). | 適切な品質管理をしている（L-2～L-5に適合）
applicable | L) Safety Critical Fastener | Safety Critical Fastener | ー | Safety Critical Fastenerがあるか？
| L-1-1) Secondary Locking Feature | L-1-1b) Locking compound of which the application process MUA is approved. | ②Loctite263 [Phase 012] Closed, Document No. :06_BIRDSX(DRAGONFLY)-AP-01 Assembly Procedure(2024/6/7) [Phase 3] Closed, Document No. :18_DRAGONFLY-AR-01 Assembly Record (2024/03/16) | 以下のいずれかの２次ゆるみ止めを有する ①摩擦型OR非摩擦型のゆるみ止め機構（ランニングトルクの計測を含む） ②MUA承認実績のある工程によるロッキングコンパウンド または、MWLとMEFLを考慮した振動試験をパスしている。 なお、キット品利用の場合；キット品のみではなく、衛星システムに対して実施
| L-2-1) Certificates for fastener materials | L-2-1) Certificates for fastener materials | [Phase 3] Closed, Document No. :18_DRAGONFLY-AR-01 Assembly Record (2024/03/16) | ファスナの材料証明 または、MWLとMEFLを考慮した振動試験をパスしている。 なお、キット品利用の場合；キット品のみではなく、衛星システムに対して実施
| L-3) Torque mark inspection | L-3) Torque mark inspection | [Phase 012] Closed, Document No. :06_BIRDSX(DRAGONFLY)-AP-01 Assembly Procedure(2024/6/7) [Phase 3] Closed, Document No. :18_DRAGONFLY-AR-01 Assembly Record (2024/03/16) [Phase3] Closed, Document No. :25_DRAGONFLY-VT-01 Vibration Test Report (2024/03/21) | トルクマークにより緩みがないことを確認している
| L-4) Fastening torque control | L-4) Fastening torque control | [Phase 012] Closed, Document No. :06_BIRDSX(DRAGONFLY)-AP-01 Section4.1.7 Assembly Procedure(2024/03/15) [Phase 3] Closed, Document No. :18_DRAGONFLY-AR-01 Assembly Record (2024/03/16) | トルク管理している
| L-5) Fastener traceability | L-5) Fastener traceability |  | 材料証明のあるファスナを設計どおり使用している
applicable | M) Sealed Container | Sealed Container | ー | Sealed Containerがあるか？
| M-1) Container characteristic | Single, Independent Container containing a non-hazardous substance. |  | Single, Independent Container containing a non-hazardous substance.
| M-2) Stored Energy | Contain less than 19,310 Joules(14,240 foot-pounds) of stored energy |  | Contain less than 19,310 Joules(14,240 foot-pounds) of stored energy
| M-3) Maximum delta pressure | Maximum delta pressure is less than 1.5atm(22psia, 1.5bars) |  | less than 1.5atm(22psia, 1.5bars)
applicable | N) Fracture Critical Part | Fracture Critical Part | ー | Fracture Critical Partがあるか？（Solar cellカバーガラスおよびカメラレンズはH)に該当）
| N-1) Design Verification | Verified by Structural Analysis with appropriate mechanical properties | [Phase012] Closed, Document No. :02_BIRDSX(DRAGONFLY)-SR-01 Section 5.4 Structural Analysis Report (2024/5/28) | 構造解析（強度・剛性）に用いる機械的特性データが妥当であるか確認する。
| N-2) Production Verification | Verified by appropriate material selection and production process | [Phase 3] Closed, Document No. :18_DRAGONFLY-AR-01 Assembly Record (2024/03/16) | 適切な製造装置および材料で、製作されていることを確認する
| N-3) Product Verification | Verified by visual inspection after vibration test under the condition specified in JX-ESPC-101132/101133 Visual Inspection and NDE(Tapping test acceptable) before and after Tests | [Phase3] Closed, Document No. :25_DRAGONFLY-VT-01 Vibration Test Report (2024/03/21) | フライト品(特に搭載部品との複雑な結合部等)が健全に製作されていることを確認する なお、キット品利用の場合；キット品のみではなく、衛星システムに対して実施